LEAP AUTO PARTS MARKETPLACE

Project Kickoff Charter & Readiness Checklist

Version 1.1  ·  Draft for kickoff  ·  16-week Phase 1 timeline  ·  July 12, 2026

This document turns the Software Requirements Specification and UI prototypes into an actionable starting point: the decisions that need sign-off, the people and vendors to line up, the legal and compliance groundwork, the accounts to open, and the checklists to run the kickoff meeting from. Each table is meant to be used directly — assign an owner and a date, then check items off as they close.

# 1. Open Decisions Requiring Sign-Off

These block accurate scoping and estimation — resolve before or during kickoff. They carry over from the SRS Appendix (Section 11).

| Decision needed | Options | Owner | Due |
| --- | --- | --- | --- |
| Mobile development approach | React Native / Flutter (recommended for budget & timeline) vs. native iOS + Android | Product + Tech Lead | Kickoff |
| Phase 1 launch countries | Pick 3–5 priority countries rather than a simultaneous global launch | Product / Sponsor | Kickoff |
| Fitment data source | Supplier-provided only vs. licensed ACES/PIES-compatible data provider | Product + Ops | Week 1 |
| Shipping / 3PL partner(s) | China→destination carrier options, cost, and delivery lead times | Ops / Logistics | Week 2 |
| Payment methods per country | Stripe/PayPal/Google Pay + which local methods (Mada, Alipay, iDEAL, etc.) | Finance + Tech Lead | Week 2 |
| Commission structure | Flat rate vs. per-category vs. per-supplier vs. per-country | Finance / Sponsor | Week 2 |
| Return & warranty policy | Window length, who bears return shipping, warranty duration by category | Product / Legal | Week 2 |
| Guest checkout | Allowed without an account, or account required | Product | Week 1 |
| Translation review level | Machine translation only vs. human review for top SKUs, and which languages | Product / Ops | Week 3 |
| Tax / VAT / customs approach | In-house rules engine vs. third-party tax-calculation service (e.g., Avalara) | Finance / Legal | Week 3 |

# 2. Team & Vendor Setup

## 2.1 Staffing decision

Decide the delivery model before writing job posts or RFPs: in-house hires, a single development agency, or a mix of freelancers coordinated by an internal PM. If going the agency route, the SRS and the three UI prototypes (mobile app, admin dashboard, supplier portal) are ready to use as the RFP/scoping package — send them out for comparable quotes.

## 2.2 Core roles needed either way

|  | Item | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| ☐ | Project / Product Manager | Sponsor | Kickoff | Not started |
| ☐ | Backend / API engineer(s) | Tech Lead | Week 1 | Not started |
| ☐ | Mobile engineer(s) (per chosen framework) | Tech Lead | Week 1 | Not started |
| ☐ | Frontend engineer (admin backend + supplier portal) | Tech Lead | Week 1 | Not started |
| ☐ | QA / test engineer | Tech Lead | Week 2 | Not started |
| ☐ | DevOps / infrastructure owner | Tech Lead | Week 1 | Not started |
| ☐ | UI/UX designer (polish pass on prototypes) | Product | Week 2 | Not started |

# 3. Legal & Compliance

|  | Item | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| ☐ | Confirm/register the legal entity operating the platform | Sponsor / Legal | Week 1 | Not started |
| ☐ | Draft Terms of Service | Legal | Week 3 | Not started |
| ☐ | Draft Privacy Policy (per launch-country data law) | Legal | Week 3 | Not started |
| ☐ | Draft Supplier / Seller Agreement (commission, SLAs, disputes) | Legal | Week 3 | Not started |
| ☐ | Draft Return & Warranty Policy | Legal / Product | Week 3 | Not started |
| ☐ | Confirm data-protection compliance approach per launch country (GDPR/CCPA/PDPL/etc.) | Legal | Week 2 | Not started |
| ☐ | Confirm tax/VAT registration needs per launch country | Finance / Legal | Week 3 | Not started |
| ☐ | Confirm import/customs disclosure requirements for cross-border shipping | Legal / Logistics | Week 3 | Not started |

# 4. Accounts & Infrastructure to Set Up

Several of these have real lead times — payment gateway and app-store accounts especially can take days to weeks to approve. Start these in week 1, in parallel with development setup.

|  | Item | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| ☐ | Cloud provider account (AWS / GCP / Azure) | DevOps | Week 1 | Not started |
| ☐ | Domain name + DNS | DevOps | Week 1 | Not started |
| ☐ | Payment gateway merchant accounts (Stripe, PayPal, etc.) | Finance | Week 1 | Not started |
| ☐ | Region-specific payment method approvals (e.g., Mada) | Finance | Week 2 | Not started |
| ☐ | Apple Developer Program account | Tech Lead | Week 1 | Not started |
| ☐ | Google Play Console account | Tech Lead | Week 1 | Not started |
| ☐ | SMS / email / push notification provider | DevOps | Week 2 | Not started |
| ☐ | Machine translation API account | Tech Lead | Week 2 | Not started |
| ☐ | Tax-calculation service account (if selected in Section 1) | Finance | Week 3 | Not started |
| ☐ | Error tracking / analytics tooling | DevOps | Week 2 | Not started |

# 5. Supplier Readiness

|  | Item | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| ☐ | Finalize Supplier Agreement template (see Section 3) | Legal / Ops | Week 3 | Not started |
| ☐ | Identify first batch of verified suppliers to onboard at launch | Ops | Week 3 | Not started |
| ☐ | Confirm fitment/product data source per Section 1 decision | Ops | Week 2 | Not started |
| ☐ | Prepare supplier bulk-upload template and instructions (Chinese) | Ops / Tech Lead | Week 4 | Not started |
| ☐ | Define supplier fulfillment SLA and escalation process | Ops | Week 3 | Not started |

# 6. Content & Brand Assets

|  | Item | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| ☐ | Finalize master category taxonomy | Product | Week 2 | Not started |
| ☐ | Translate legal/policy content into launch-country languages | Legal / Ops | Week 4 | Not started |
| ☐ | Finalize logo, icon set, and brand guidelines (design polish pass on prototype system) | Design | Week 4 | Not started |
| ☐ | Prepare Help Center / FAQ content | Product / Support | Week 5 | Not started |

# 7. Project Governance

## 7.1 Kickoff meeting agenda

Suggested 90-minute kickoff agenda once the team is assembled:

- Walk through the SRS and the three prototypes (mobile app, admin dashboard, supplier portal) with the full team.

- Work through Section 1 (Open Decisions) live and assign owners/dates for anything not yet resolved.

- Confirm the Phase 1 scope boundary (Must Have requirements only) and explicitly agree what is out of scope for launch.

- Assign owners for Sections 2–6 of this checklist.

- Set the cadence for recurring check-ins (recommended: weekly status, bi-weekly demo).

## 7.2 Milestone plan (16-week Phase 1 window)

16 weeks (≈ 3.7 months) is tighter than the 5–6 month window assumed in the SRS budget/timeline note. Hitting it requires strict discipline on scope: Must Have requirements only, no mid-project scope additions, and country/language coverage limited to the priority set agreed in Section 1. Flag slippage early rather than quietly extending scope.

|  | Item | Owner | Target date | Status |
| --- | --- | --- | --- | --- |
| ☐ | Milestone 1: Decisions closed, team + vendors onboarded, accounts provisioned | Sponsor / PM | End of Week 2 | Not started |
| ☐ | Milestone 2: Core services (catalog, cart, order, payment) functional in dev | Tech Lead | Week 7 | Not started |
| ☐ | Milestone 3: Supplier portal + admin backend functional; first suppliers onboarded | Ops / Tech Lead | Week 11 | Not started |
| ☐ | Milestone 4: End-to-end QA pass across buyer app, admin, and supplier portal | QA | Week 14 | Not started |
| ☐ | Milestone 5: Phase 1 launch in priority countries | PM / Sponsor | Week 16 | Not started |

## 7.3 Success metrics to track from launch

These map directly to the KPIs already modeled in the admin dashboard prototype, so reporting is available from day one:

- GMV and order volume, by country

- Supplier fulfillment SLA and dispute/return rate

- Fitment search success rate (searches that return a confirmed-fit result)

- Cart abandonment and checkout conversion rate